## Slide 1: District Utility Program Meeting
District 3
October 10, 2023
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 2: This meeting is being recorded
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 3: Welcome
Before we begin, let’s have a brief safety moment.
Virtual Attendees
Unmute yourself or use your chat box if you are in an emergency situation.
In-Person Attendees
Emergency Exits
Tornado Shelter
911 Caller
AED Location
Restrooms
Notes: NDOT Utility Coordinator (In-person safety briefing)
HDR (Kristen, Amanda or Alyssa) (Virtual safety briefing)

## Slide 4: Agenda
Introductions
Utility Program Updates
Construction Activities vs. Utility Conflicts
Construction Projects Review
  Outstanding 2023 Construction Projects
  2024 Construction Projects
  2025 Construction Projects
Questions & Wrap Up
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 5: Introductions
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 6: Introduce Yourself
Introduce yourself and share:
Name
Organization
Role
Favorite Pizza Topping
In-Person Attendees
Please go around the room and introduce yourself.
Virtual Attendees
Please type the information in the chat box.
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 7: Utility Program Updates
Notes: Jamie Mikkleson

## Slide 8: Key Outcome
To improve utility coordination from Design through Construction.
Notes: Jamie Mikkleson

## Slide 9: Improvement Emphasis
Communication during planning and construction
Improved utility data collection and plan presentation
Construction schedule coordination
Notes: Jamie Mikkleson

## Slide 10: Ndot utility section
Notes: Jamie Mikkleson

## Slide 11: Utilities Organization Structure
Kyle Keller
Katie Acevedo
Katharine Fischer
Don Horton
Rhett Robinson
Dave Hansen
Curt Yager
Districts 1 & 8
Districts 2 & 3
District 4
Districts 5, 6, & 7
Notes: Jamie Mikkleson

## Slide 12: Program level updates
Notes: Jamie Mikkleson

## Slide 13: Accommodation Policy
Sets forth guidelines & requirements for accommodating utility facilities within State Highway Property
In process of completely revamping the policy
Notes: Jamie Mikkleson

## Slide 14: Accommodation Policy
Current Step
Review & comment phase
Next Step
Implementation phase
Internal & FHWA concurrent review
Internal implementation & Stakeholder outreach
Notes: Jamie Mikkleson

## Slide 15: Policy – key changes
Depth of bury by facility type
Update casing requirements for steel pipelines
Outlines NDOT utility coordination process
Expand construction and maintenance requirements
Identifies construction plan and ‘As-Installed’ plan requirements
Addresses change in ownership and abandoned or out of service facilities
Broadband chapter
Notes: Jamie Mikkleson

## Slide 16: Project level updates
Notes: Jamie Mikkleson

## Slide 17: Utility questionnaire
Receive via email from NDOT Utility Coordinator
Action by Utility Company required: ​
  Review and provide information for existing facility locations​
  Review existing locations for construction conflicts, both temporary and permanent conflicts​
Transmit responses and supporting documentation back to NDOT​
NDOT will track unresponsive utility companies & continue to follow up
Notes: Jamie Mikkleson

## Slide 18: Conflict analysis process
Utility Company will perform Conflict Analysis​
  ​Review for conflicts with:
    Final construction – limits of construction, ROW, ditch grading
    Temporary construction – drives, access crossings, phasing
  NDOT will review analysis and work with Utility Company
If relocations are required, Utility Company will provide relocation information: ​
  Scope of work​
  Detailed cost estimate​
  Schedule of relocation work​
Notes: Jamie Mikkleson

## Slide 19: Relocation process
NDOT will review and provide comments on relocation plans and detailed cost estimate​
  Will be incorporated into the agreement
Master (Blanket) Agreement or Utility Project Agreement​
  Only if relocation is reimbursable
Letter of Authorization
  Every relocation
Notes: Jamie Mikkleson

## Slide 20: 2024 Goals
Implement Utility Accommodation Policy
Identify utility conflicts early
Coordinate utility relocations to be complete by construction start
Professional development of coordinator staff
2024 District Utility Program Meetings – October
Notes: Jamie Mikkleson

## Slide 21: Activities vs. conflicts
When we say… | Think about…
Access Crossings – Contractor ~Pipes or Temp. Bridge | Cranes and large equipment Impacts or proximity to overhead power Piling for temporary bridge
Shoo-flys – Traffic | In addition to access crossings Additional fill Impacts to pedestals, pull boxes, overhead power, etc.
Grade beam on pile | Cranes Impacts or proximity to overhead power
Over-excavation | Possibility on any project Most likely at culverts and locations of known muck
Notes: Jamie Mikkleson

## Slide 22: Activities vs. conflicts
When we say… | Think about…
Concrete Box Culverts | Sheet pile driven at wingwalls Impacts to buried lines Impacts or proximity to overhead power Temporary shoring on phased construction
Culvert Replacements – Phased construction | Potential for temporary shoring Need room (H & V) to construct end treatments
Culvert Replacements – Jacking | Large jacking pits - ~50’x100’, not shown in plans Temporary excavation down to flowline to construct Need room (H & V) to construct end treatments
Notes: Jamie Mikkleson

## Slide 23: Activities vs. conflicts
When we say… | Think about…
Temporary Roads & Drives | Can require grading and ditch work Similar impacts to permanent construction
Guardrail | Posts can impact underground facilities
Sidewalk & ADA work | Pavement removal Shallow service lines
Curb Inlets | 3 ft – 6 ft deep, in most cases Cast in place inlets require extra room for form work
Notes: Jamie Mikkleson

## Slide 24: Construction Projects Review
District 3

## Slide 25: Outstanding Construction Year 2023
The following projects will likely not be completed in 2023

## Slide 26: 23rd St, Columbus (LET) Project NO.: NH-30-5(134); Control NO.: 32234
Project Length: 2.7
Scope of Work:
  Urban Reconstruction

## Slide 27: 23rd St, Columbus (LET) Project NO.: NH-30-5(134); Control NO.: 32234
Status: Awarded
Right-of-Way: Completed
Traffic Impacts:
  Phase Traffic Control
  Local Detour
Letting Date: 4/7/2022
Construction Timing: Currently in Construction

## Slide 28: 23rd St, Columbus (LET) Project NO.: NH-30-5(134); Control NO.: 32234
Anticipated Utilities Impact:
  Urban Recon
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy, Charter Comm. (Spectrum), City of Columbus, Cornhusker PPD, Eagle Comm., Frontier Comm., Great Plains Comm., Loup River PPD, Lumen (CenturyLink), Midstates Data Transport, Nebraska PPD

## Slide 29: Decatur - Macy (LET) Project NO.: STP-75-3(118); Control NO.: 32139
Project Length: 7.7
Scope of Work:
  Resurfacing
  Guardrail
  Culvert Extension/Replace

## Slide 30: Decatur - Macy (LET) Project NO.: STP-75-3(118); Control NO.: 32139
Status: Awarded
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 3/2/2023
Construction Timing: Currently in Construction

## Slide 31: Decatur - Macy (LET) Project NO.: STP-75-3(118); Control NO.: 32139
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Bridge Repair/Replacement
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Burt County PPD, Fastwyre Broadband (ABB), Lumen (CenturyLink), Northeast Nebr. Telephone Co., Village of Decatur

## Slide 32: Construction Year 2024
The following projects are anticipated to be let during 2024

## Slide 33: N. Jct. N-51 - S. Jct. N-9 (MS) Project NO.: STP-16-3(110); Control NO.: 32289
Project Length: 10.3
Scope of Work:
  Resurfacing
  Bridge Replacement
  Guardrail

## Slide 34: N. Jct. N-51 - S. Jct. N-9 (MS) Project NO.: STP-16-3(110); Control NO.: 32289
Status: Preparing for Bid
Right-of-Way: Completed
Traffic Impacts:
  Full Detour
  Phase Traffic Control
Letting Date: 10/19/2023
Construction Timing: 6/17/2024

## Slide 35: N. Jct. N-51 - S. Jct. N-9 (MS) Project NO.: STP-16-3(110); Control NO.: 32289
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  No K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy, Cuming County PPD, Cuming County RWD 1, Great Plains Comm., Nebraska PPD, Village of Bancroft

## Slide 36: US-20 - N-59 Project NO.: STP-14-4(117); Control NO.: 32284
Project Length: 8.3
Scope of Work:
  Resurfacing
  Shoulder Work
  Guardrail

## Slide 37: US-20 - N-59 Project NO.: STP-14-4(117); Control NO.: 32284
Status: Preparing for Bid
Right-of-Way: Completed
Traffic Impacts:
  Phase Traffic Control
Letting Date: 12/14/2023
Construction Timing: 7/8/2024

## Slide 38: US-20 - N-59 Project NO.: STP-14-4(117); Control NO.: 32284
Anticipated Utilities Impact:
  Shoulder Work
  Guardrail
  Lighting
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  AT&T Comm., Great Plains Comm., North Central PPD, Northeast Nebr. Telephone Co.

## Slide 39: Lyons - Walthill (MS) Project NO.: NH-77-3(126); Control NO.: 31922
Project Length: 17.7
Scope of Work:
  Resurfacing
  Culvert Extension/Replace
  Guardrail

## Slide 40: Lyons - Walthill (MS) Project NO.: NH-77-3(126); Control NO.: 31922
Status: Design
Right-of-Way: Completed
Traffic Impacts:
  Phase Traffic Control
Letting Date: 5/16/2024
Construction Timing: 8/1/2024

## Slide 41: Lyons - Walthill (MS) Project NO.: NH-77-3(126); Control NO.: 31922
Anticipated Utilities Impact:
  Shoulder Work
  Culvert Extension/Replacement
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  No K-Sheets Required
  Special Provisions Required
Utilities Involved:
  AT&T Comm., Burt County PPD, , City of Lyons, Lower Elkhorn NRD, Lumen (CenturyLink), Nebraska PPD, Zayo Group

## Slide 42: Pender - Emerson (MS) Project NO.: STP-9-4(116); Control NO.: 32136
Project Length: 12.1
Scope of Work:
  Resurfacing
  Culvert Extension/Replace
  Guardrail

## Slide 43: Pender - Emerson (MS) Project NO.: STP-9-4(116); Control NO.: 32136
Status: Design
Right-of-Way: Completed
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/1/2024
Construction Timing: 3/11/2024

## Slide 44: Pender - Emerson (MS) Project NO.: STP-9-4(116); Control NO.: 32136
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Culvert Extension/Replacement
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, City of Pender, Fastwyre Broadband (ABB), Great Plains Comm., Lumen (CenturyLink), Middle Missouri Tribes NRD, Northeast Power, Northern Natural Gas, Papio-Missouri, Skywave Wireless, Thurston County Rural Water, Village of Emerson, Village of Pender, Village of Thurston

## Slide 45: N-12 North & South Project NO.: STP-NH-15-4(122); Control NO.: 32288
Project Length: 9.3
Scope of Work:
  Resurfacing
  Shoulder Work
  Guardrail

## Slide 46: N-12 North & South Project NO.: STP-NH-15-4(122); Control NO.: 32288
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/1/2024
Construction Timing: 7/15/2024

## Slide 47: N-12 North & South Project NO.: STP-NH-15-4(122); Control NO.: 32288
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  New ROW
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Cedar Vision Inc, Cedar-Knox PPD, City of Hartington, Great Plains Comm., Hartelco, Lumen (CenturyLink), Northeast Nebr. Telephone Co., Northeast Power

## Slide 48: US-81/N Main St Near Madison Project NO.: HSIP-81-3(147); Control NO.: 32350
Project Length: 0
Scope of Work:
  Full Depth Pavement
  Grading

## Slide 49: US-81/N Main St Near Madison Project NO.: HSIP-81-3(147); Control NO.: 32350
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/1/2024
Construction Timing: 7/29/2024

## Slide 50: US-81/N Main St Near Madison Project NO.: HSIP-81-3(147); Control NO.: 32350
Anticipated Utilities Impact:
  Full Depth Pavement
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  No K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy, City of Madison, Frontier Comm., Great Plains Comm., Sparklight Fiber (Cable One)

## Slide 51: In Stanton & North Project NO.: STP-57-3(111); Control NO.: 32359
Project Length: 5
Scope of Work:
  Resurfacing
  Grading
  Urban Reconstruction

## Slide 52: In Stanton & North Project NO.: STP-57-3(111); Control NO.: 32359
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/29/2024
Construction Timing: 6/10/2024

## Slide 53: In Stanton & North Project NO.: STP-57-3(111); Control NO.: 32359
Anticipated Utilities Impact:
  Grading
  Culvert Extension/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy, City of Stanton, Great Plains Comm., Lumen (Century Link), Sparklight Fiber (Cable One), Stanton County PPD, Stanton Telecom., Tallgrass Energy

## Slide 54: In Norfolk Traffic Signals Project NO.: HSIP-81-3(150); Control NO.: 32363
Project Length: 5.3
Scope of Work:
  Misc.

## Slide 55: In Norfolk Traffic Signals Project NO.: HSIP-81-3(150); Control NO.: 32363
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/1/2024
Construction Timing: 4/1/2024

## Slide 56: In Norfolk Traffic Signals Project NO.: HSIP-81-3(150); Control NO.: 32363
Anticipated Utilities Impact:
  Lighting
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  K-Sheets TBD
  Special Provisions Required
Utilities Involved:
  Allo Comm., Black Hills Energy, City of Norfolk, Lumen (CenturyLink), Midstates Data Trasnport, Nebraska DEQ, Nebraska PPD, NuStar Pipeline, Pierce Telephone Co., Sparklight Internet (CableOne), Unite Private Networks, USCOC N-K

## Slide 57: Santee South Bridge (MS) Project NO.: STP-S54D(104); Control NO.: 32278
Project Length: 0
Scope of Work:
  Bridge Replacement
  Guardrail
  Access X-ings & Shoo-Fly

## Slide 58: Santee South Bridge (MS) Project NO.: STP-S54D(104); Control NO.: 32278
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/29/2024
Construction Timing: 6/3/2024

## Slide 59: Santee South Bridge (MS) Project NO.: STP-S54D(104); Control NO.: 32278
Anticipated Utilities Impact:
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  K-Sheets: K-Sheets Required
  Special Provisions: Special Provisions Required
Utilities Involved:
  Bureau of Indian Affairs, Great Plains Comm., North Central PPD

## Slide 60: Wausa North Project NO.: STP-121-4(116); Control NO.: 32379
Project Length: 7.1
Scope of Work:
  Resurfacing

## Slide 61: Wausa North Project NO.: STP-121-4(116); Control NO.: 32379
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 5/16/2024
Construction Timing: 8/26/2024

## Slide 62: Wausa North Project NO.: STP-121-4(116); Control NO.: 32379
Anticipated Utilities Impact:
  Shoulder Work
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Cedar-Knox PPD, Great Plains Comm., Village of Wausa, WAPA

## Slide 63: Columbus South Bridges Project NO.: NH-30-5(131); Control NO.: 31983
Project Length: 0
Scope of Work:
  Bridge Replacement
  Full Depth Pavement
  Urban Reconstruction

## Slide 64: Columbus South Bridges Project NO.: NH-30-5(131); Control NO.: 31983
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 7/25/2024
Construction Timing: 9/23/2024

## Slide 65: Columbus South Bridges Project NO.: NH-30-5(131); Control NO.: 31983
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Guardrail
  Lighting
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  K-Sheets TBD
  Special Provisions Required
Utilities Involved:
  Allo Comm., Black Hills Energy, City of Columbus, Frontier Comm., Great Plains Comm., Loup River PPD, Lumen (CenturyLink)

## Slide 66: I-129 over Missouri River, So. Sioux City Project NO.: STR-129-1(1016); Control NO.: 32416
Project Length: 0
Scope of Work:
  Bridge Repair

## Slide 67: I-129 over Missouri River, So. Sioux City Project NO.: STR-129-1(1016); Control NO.: 32416
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Other
Letting Date: 12/19/2023
Construction Timing: 3/1/2024

## Slide 68: I-129 over Missouri River, So. Sioux City Project NO.: STR-129-1(1016); Control NO.: 32416
Anticipated Utilities Impact:
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  City of South Sioux City, Mid American Energy, Sparklight Internet (CableOne)

## Slide 69: Construction Year 2025
The following projects are anticipated to be let during 2025

## Slide 70: Macy - Winnebago (MS) Project NO.: STP-75-4(115); Control NO.: 31989
Project Length: 10.3
Scope of Work:
  Resurfacing
  Shoulder Work
  Culvert Extension/Replace

## Slide 71: Macy - Winnebago (MS) Project NO.: STP-75-4(115); Control NO.: 31989
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/19/2025

## Slide 72: Macy - Winnebago (MS) Project NO.: STP-75-4(115); Control NO.: 31989
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Guardrail
  Shoulder Work
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
  Potholing TBD
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Burt County PPD, Fastwyre Broadband (ABB), Great Plains Comm., Lumen (CenturyLink), Nebraska PPD, Omaha Tribe of NE, Village of Winnebago, Winnebago Tribe of NE

## Slide 73: Monroe East & West (MS) Project NO.: STP-22-5(119); Control NO.: 32292
Project Length: 13.2
Scope of Work:
  Resurfacing
  Bridge Replacement
  Urban Reconstruction

## Slide 74: Monroe East & West (MS) Project NO.: STP-22-5(119); Control NO.: 32292
Status: Design
Right-of-Way: Completed
Traffic Impacts:
  Phase Traffic Control
  Local Detour
Letting Date: 8/29/2024
Construction Timing: 3/17/2025

## Slide 75: Monroe East & West (MS) Project NO.: STP-22-5(119); Control NO.: 32292
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Grading
  New ROW
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
  Locates
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Cornhusker PPD, Frontier Comm., Kinder Morgan, Loup River PPD, Northeast Nebr. Telephone Co., Village of Monroe

## Slide 76: N-57 - East Jct N-15 Project NO.: TIB-275-6(149); Control NO.: 32319A
Project Length: 11.8
Scope of Work:
  Full Depth Pavement
  Bridge Replacement
  Grading

## Slide 77: N-57 - East Jct N-15 Project NO.: TIB-275-6(149); Control NO.: 32319A
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 4/1/2025

## Slide 78: N-57 - East Jct N-15 Project NO.: TIB-275-6(149); Control NO.: 32319A
Anticipated Utilities Impact:
  Full Depth Pavement
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
  Locates
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy, Cuming County PPD, Great Plains Comm., Lumen (CenturyLink), Stanton County PPD, Stanton Telecom

## Slide 79: Madison North Project NO.: NH-81-3(149); Control NO.: 32357
Project Length: 6.6
Scope of Work:
  Resurfacing
  Culvert Extension/Replace
  Guardrail

## Slide 80: Madison North Project NO.: NH-81-3(149); Control NO.: 32357
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/12/2025

## Slide 81: Madison North Project NO.: NH-81-3(149); Control NO.: 32357
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Guardrail
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Potholing TBD
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, City of Madison, Elkhorn Rural PPD, Frontier Comm., Great Plains Comm., Lumen (CenturyLink), Midstates Data Trasnport , Nebraska PPD, Sparklight Internet (CableOne)

## Slide 82: Laurel - N-116 Project NO.: NH-20-6(112); Control NO.: 32358
Project Length: 7.9
Scope of Work:
  Resurfacing
  Bridge Replacement
  Guardrail

## Slide 83: Laurel - N-116 Project NO.: NH-20-6(112); Control NO.: 32358
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 6/30/2025

## Slide 84: Laurel - N-116 Project NO.: NH-20-6(112); Control NO.: 32358
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Culvert Extension/Replacement
  Temp. Roads/Drives
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Cedar Knox PPD, City of Laurel, Fastwyre Broadband (ABB), Great Plains Comm., Lower Elkhorn NRD, Lumen (Century Link), Northeast Nebr. Telephone Co., Northeast Power

## Slide 85: Silver Creek - Duncan Project NO.: NH-30-5(138); Control NO.: 32366
Project Length: 10.1
Scope of Work:
  Resurfacing
  Urban Reconstruction
  Guardrail

## Slide 86: Silver Creek - Duncan Project NO.: NH-30-5(138); Control NO.: 32366
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 4/1/2025

## Slide 87: Silver Creek - Duncan Project NO.: NH-30-5(138); Control NO.: 32366
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Guardrail
  Shoulder Work
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Arvig Enterprises (Tekstar Comm.), Cornhusker PPD, Frontier Comm., Loup River PPD, Lumen (CenturyLink), Midstates Data Trasnport , Northeast Nebr. Telephone Co., NuStar Pipeline, Polk County Rural PPD, Village of Duncan, Village of Silver Creek, Vyve Broadband

## Slide 88: Homer North Project NO.: NH-HSIP-75-4(116); Control NO.: 32377
Project Length: 5.5
Scope of Work:
  Shoulder Work

## Slide 89: Homer North Project NO.: NH-HSIP-75-4(116); Control NO.: 32377
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 7/28/2025

## Slide 90: Homer North Project NO.: NH-HSIP-75-4(116); Control NO.: 32377
Anticipated Utilities Impact:
  Shoulder Work
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Dakota County Rural Water, Fastwyre Broadband (ABB), Great Plains Comm., Lumen (CenturyLink), Nebraska PPD, Northeast Power, Northern Natural Gas, Verizon / MCI

## Slide 91: SW of Hubbard - US-75/77 Project NO.: NH-35-4(127); Control NO.: 32150A
Project Length: 9.4
Scope of Work:
  Resurfacing
  Shoulder Work
  Grading

## Slide 92: SW of Hubbard - US-75/77 Project NO.: NH-35-4(127); Control NO.: 32150A
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 10/3/2024
Construction Timing: 5/1/2025

## Slide 93: SW of Hubbard - US-75/77 Project NO.: NH-35-4(127); Control NO.: 32150A
Anticipated Utilities Impact:
  Guardrail
  Culvert Extension/Replacement
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
  Potholing TBD
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  City of Dakota City, Great Plains Comm., Lumen (CenturyLink), Mid American Energy, Nebraska PPD, Northeast Nebr. Telephone Co., Northeast Power, Northern Natural Gas, Papio-Missouri, Sparklight Internet (CableOne), Verizon / MCI, Village of Hubbard

## Slide 94: Orchard East & West (MS) Project NO.: NH-20-5(113); Control NO.: 32291
Project Length: 8.8
Scope of Work:
  Urban Reconstruction
  Resurfacing
  Shoulder Work

## Slide 95: Orchard East & West (MS) Project NO.: NH-20-5(113); Control NO.: 32291
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 11/7/2024
Construction Timing: 7/28/2025

## Slide 96: Orchard East & West (MS) Project NO.: NH-20-5(113); Control NO.: 32291
Anticipated Utilities Impact:
  Shoulder Work
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Frontier Comm., Great Plains Comm., North Central PPD, Village of Orchard, Village of Royal

## Slide 97: Niobrara East & West Project NO.: S-12-5(1011); Control NO.: 31674
Project Length: 10.6
Scope of Work:
  Full Depth Pavement
  Guardrail
  Bridge Replacement

## Slide 98: Niobrara East & West Project NO.: S-12-5(1011); Control NO.: 31674
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 12/12/2024
Construction Timing: 5/1/2025

## Slide 99: Niobrara East & West Project NO.: S-12-5(1011); Control NO.: 31674
Anticipated Utilities Impact:
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
  Utilities Workshop
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Great Plains Comm., North Central PPD, Santee Tribe, U.S. Army Corps of Engineers, Village of Niobrara

## Slide 100: Ponca - US-20 Project NO.: STP-12-6(119); Control NO.: 32352
Project Length: 8.2
Scope of Work:
  Resurfacing
  Bridge Replacement
  Guardrail

## Slide 101: Ponca - US-20 Project NO.: STP-12-6(119); Control NO.: 32352
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 12/12/2024
Construction Timing: 3/3/2025

## Slide 102: Ponca - US-20 Project NO.: STP-12-6(119); Control NO.: 32352
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Culvert Extension/Replacement
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy, City of Ponca, Great Plains Comm., Northeast Nebr. Telephone Co., Northeast Power, Sparklight Fiber (Cable One)

## Slide 103: Macy Intersection Project NO.: DPS-75-4(118); Control NO.: 32415
Project Length: 0
Scope of Work:
  Urban Reconstruction
  Full Depth Pavement
  Grading

## Slide 104: Macy Intersection Project NO.: DPS-75-4(118); Control NO.: 32415
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 3/6/2025
Construction Timing: 5/1/2025

## Slide 105: Macy Intersection Project NO.: DPS-75-4(118); Control NO.: 32415
Anticipated Utilities Impact:
  New Alignment
Anticipated Request from Utilities:
  Utilities Workshop
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Burt County PPD, Fastwyre Broadband (ABB), Omaha Tribe of NE

## Slide 106: West Point East Project NO.: STP-HSIP-32-6(116); Control NO.: 32404
Project Length: 1.7
Scope of Work:
  Resurfacing
  Full Depth Pavement
  Guardrail

## Slide 107: West Point East Project NO.: STP-HSIP-32-6(116); Control NO.: 32404
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 5/15/2025
Construction Timing: 6/23/2025

## Slide 108: West Point East Project NO.: STP-HSIP-32-6(116); Control NO.: 32404
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets TBD
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, City of Westpoint, Cuming County PPD, Cuming County RDW 1, Great Plains Comm., Lumen (CenturyLink), Skywave Wireless

## Slide 109: East Jct N-15 - Wisner Project NO.: TIB-275-6(150); Control NO.: 32319B
Project Length: 4.2
Scope of Work:
  Full Depth Pavement
  Grading

## Slide 110: East Jct N-15 - Wisner Project NO.: TIB-275-6(150); Control NO.: 32319B
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/28/2025
Construction Timing: 10/1/2025

## Slide 111: East Jct N-15 - Wisner Project NO.: TIB-275-6(150); Control NO.: 32319B
Anticipated Utilities Impact:
  Grading
  Temp. Roads/Drives
  New ROW
Anticipated Request from Utilities:
  Utilities Workshop
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  City of Wisner, Cuming County PPD, Cuming County RWD 1, Great Plains Comm., Lumen (CenturyLink), Tallgrass Energy

## Slide 112: Questions & Wrap Up
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 113: Any final Questions?
Ask them now!
If you have questions after this meeting, or would like to view more detailed project maps, please reach out to your utility coordinator.
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 114: Have a Question about a project your Utility is involved in?
Contact your district’s utility coordinator!
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 115: We need your feedback
Your valuable feedback helps these meetings – and NDOT’s utility coordination program – be better.
Use your phone’s camera to scan this QR code or use our paper survey.
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 116: Visit our Website
Visit NDOT.info/utility for more information on:
Utility accommodation
Permitting
Coordination
Project information
Reimbursements
Additional information
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 117: Thank You
Notes: HDR (Kristen, Amanda or Alyssa)