## Slide 1: District Utility Program Meeting
District 4
October 19, 2023
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 2: This meeting is being recorded
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 3: Welcome
Before we begin, let’s have a brief safety moment.
Virtual Attendees
Unmute yourself or use your chat box if you are in an emergency situation.
In-Person Attendees
Emergency Exits
Tornado Shelter
911 Caller
AED Location
Restrooms
Notes: NDOT Utility Coordinator (In-person safety briefing)
HDR (Kristen, Amanda or Alyssa) (Virtual safety briefing)

## Slide 4: Agenda
Introductions
Utility Program Updates
Construction Activities vs. Utility Conflicts
Construction Projects Review
  Outstanding 2023 Construction Projects
  2024 Construction Projects
  2025 Construction Projects
Questions & Wrap Up
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 5: Introductions
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 6: Introduce Yourself
Introduce yourself and share:
Name
Organization
Role
Favorite Pizza Topping
In-Person Attendees
Please go around the room and introduce yourself.
Virtual Attendees
Please type the information in the chat box.
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 7: Utility Program Updates
Notes: Jamie Mikkleson

## Slide 8: Key Outcome
To improve utility coordination from Design through Construction.
Notes: Jamie Mikkleson

## Slide 9: Improvement Emphasis
Communication during planning and construction
Improved utility data collection and plan presentation
Construction schedule coordination
Notes: Jamie Mikkleson

## Slide 10: Ndot utility section
Notes: Jamie Mikkleson

## Slide 11: Utilities Organization Structure
Kyle Keller
Katie Acevedo
Katharine Fischer
Don Horton
Rhett Robinson
Dave Hansen
Curt Yager
Districts 1 & 8
Districts 2 & 3
District 4
Districts 5, 6, & 7
Notes: Jamie Mikkleson

## Slide 12: Program level updates
Notes: Jamie Mikkleson

## Slide 13: Accommodation Policy
Sets forth guidelines & requirements for accommodating utility facilities within State Highway Property
In process of completely revamping the policy
Notes: Jamie Mikkleson

## Slide 14: Accommodation Policy
Current Step
Review & comment phase
Next Step
Implementation phase
Internal & FHWA concurrent review
Internal implementation & Stakeholder outreach
Notes: Jamie Mikkleson

## Slide 15: Policy – key changes
Depth of bury by facility type
Update casing requirements for steel pipelines
Outlines NDOT utility coordination process
Expand construction and maintenance requirements
Identifies construction plan and ‘As-Installed’ plan requirements
Addresses change in ownership and abandoned or out of service facilities
Broadband chapter
Notes: Jamie Mikkleson

## Slide 16: Project level updates
Notes: Jamie Mikkleson

## Slide 17: Conflict analysis process
Utility Company will perform Conflict Analysis​
  ​Review for conflicts with:
    Final construction – limits of construction, ROW, ditch grading
    Temporary construction – drives, access crossings, phasing
  NDOT will review analysis and work with Utility Company
If relocations are required, Utility Company will provide relocation information: ​
  Scope of work​
  Detailed cost estimate​
  Schedule of relocation work​
Notes: Jamie Mikkleson

## Slide 18: Utility questionnaire
Receive via email from NDOT Utility Coordinator
Action by Utility Company required: ​
  Review and provide information for existing facility locations​
  Review existing locations for construction conflicts, both temporary and permanent conflicts​
Transmit responses and supporting documentation back to NDOT​
NDOT will track unresponsive utility companies & continue to follow up
Notes: Jamie Mikkleson

## Slide 19: Relocation process
NDOT will review and provide comments on relocation plans and detailed cost estimate​
  Will be incorporated into the agreement
Master (Blanket) Agreement or Utility Project Agreement​
  Only if relocation is reimbursable
Letter of Authorization
  Every relocation
Notes: Jamie Mikkleson

## Slide 20: 2024 Goals
Implement Utility Accommodation Policy
Identify utility conflicts early
Coordinate utility relocations to be complete by construction start
Professional development of coordinator staff
2024 District Utility Program Meetings – October
Notes: Jamie Mikkleson

## Slide 21: Activities vs. conflicts
When we say… | Think about…
Access Crossings – Contractor ~Pipes or Temp. Bridge | Cranes and large equipment Impacts or proximity to overhead power Piling for temporary bridge
Shoo-flys – Traffic | In addition to access crossings Additional fill Impacts to pedestals, pull boxes, overhead power, etc.
Grade beam on pile | Cranes Impacts or proximity to overhead power
Over-excavation | Possibility on any project Most likely at culverts and locations of known muck
Notes: Jamie Mikkleson

## Slide 22: Activities vs. conflicts
When we say… | Think about…
Concrete Box Culverts | Sheet pile driven at wingwalls Impacts to buried lines Impacts or proximity to overhead power Temporary shoring on phased construction
Culvert Replacements – Phased construction | Potential for temporary shoring Need room (H & V) to construct end treatments
Culvert Replacements – Jacking | Large jacking pits - ~50’x100’, not shown in plans Temporary excavation down to flowline to construct Need room (H & V) to construct end treatments
Notes: Jamie Mikkleson

## Slide 23: Activities vs. conflicts
When we say… | Think about…
Temporary Roads & Drives | Can require grading and ditch work Similar impacts to permanent construction
Guardrail | Posts can impact underground facilities
Sidewalk & ADA work | Pavement removal Shallow service lines
Curb Inlets | 3 ft – 6 ft deep, in most cases Cast in place inlets require extra room for form work
Notes: Jamie Mikkleson

## Slide 24: Construction Projects Review
District 4

## Slide 25: Construction Year 2024
The following projects are anticipated to be let during 2024
Notes: Kathy Fischer or Rhett Robinson

## Slide 26: US-281 West, Grand Island Project No.: S-30-4(1046); Control No.: 41704
Project Length: 3.71
Scope of Work:
  Full Depth Pavement
  Grading
  ITS/Lighting

## Slide 27: US-281 West, Grand Island Project No.: S-30-4(1046); Control No.: 41704
Status: Preparing for Bid
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 9/28/2023
Construction Timing: 4/1/2024 - 11/1/2025

## Slide 28: US-281 West, Grand Island Project No.: S-30-4(1046); Control No.: 41704
Anticipated Utilities Impact:
  Urban Recon
  New ROW
  Culvert Extension/Replace
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Allo Comm., City of Grand Island, Cogent Comm. Inc. (Sprint & T-Mobile), Great Plains Comm., Lumen (CenturyLink), Northwestern Energy, OPTK Networks (NebraskaLink), Southern PPD, Unite Private Net., Verizon / MCI , Windstream Comm.

## Slide 29: Nuckolls Co Line - L85F Project No.: STP-136-5(113); Control No.: 42543
Project Length: 14.3
Scope of Work:
  Resurfacing
  Grading
  Culvert Extension/Replace

## Slide 30: Nuckolls Co Line - L85F Project No.: STP-136-5(113); Control No.: 42543
Status: Design
Right-of-Way: Completed
Traffic Impacts:
  Phase Traffic Control
Letting Date: 12/14/2023
Construction Timing: 6/24/2024

## Slide 31: Nuckolls Co Line - L85F Project No.: STP-136-5(113); Control No.: 42543
Anticipated Utilities Impact:
  Urban Reconstruction
  New ROW
  New Alignment
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy, City of Deshler, City of Hebron, Enbridge, Glenwood Telephone, Great Plains Comm., Norris PPD, NuStar Pipeline, Tallgrass Energy, Unite Private Net., Viaero Fiber Net. (NE-CO Cell.), Windstream Comm.

## Slide 32: Scotia East Project No.: STP-HSIP-22-4(113); Control No.: 42605
Project Length: 8.41
Scope of Work:
  Resurfacing
  Culvert Extension/Replace

## Slide 33: Scotia East Project No.: STP-HSIP-22-4(113); Control No.: 42605
Status: Preparing for Bid
Right-of-Way: Completed
Traffic Impacts:
  None
Letting Date: 9/28/2023
Construction Timing: 5/20/2024

## Slide 34: Scotia East Project No.: STP-HSIP-22-4(113); Control No.: 42605
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
  Locates
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Frontier Comm., Great Plains Comm., Hamilton Telecom. (NCTC), Howard Greeley RPPD, Lumen (CenturyLink), Twin Loups Irr. District, Village of Scotia

## Slide 35: Dawson Co Line - Odessa (TK) Project No.: NH-80-5(76); Control No.: 42756
Project Length: 9.25
Scope of Work:
  Bridge Replacement
  Full Depth Pavement
  Guardrail

## Slide 36: Dawson Co Line - Odessa (TK) Project No.: NH-80-5(76); Control No.: 42756
Status: Preparing for Bid
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 12/14/2023
Construction Timing: 4/1/2024 - 5/22/2026

## Slide 37: Dawson Co Line - Odessa (TK) Project No.: NH-80-5(76); Control No.: 42756
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Access Crossings
  Full Depth Pavement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
  Locates
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Charter Comm. (Spectrum), Dawson PPD, Frontier Comm., Glenwood Telephone, Great Plains Comm., Lumen (CenturyLink), Nebraska PPD, Southern PPD, Tallgrass Energy

## Slide 38: In Stromsburg Project No.: NH-81-2(155); Control No.: 42782B
Project Length: 0.87
Scope of Work:
  Urban Reconstruction
  Shoulder Work
  Culvert Extension/Replace

## Slide 39: In Stromsburg Project No.: NH-81-2(155); Control No.: 42782B
Status: Design
Right-of-Way: Completed
Traffic Impacts:
  Full Detour
  Local Detour
Letting Date: 12/14/2023
Construction Timing: 4/1/2025 - 10/31/2025

## Slide 40: In Stromsburg Project No.: NH-81-2(155); Control No.: 42782B
Anticipated Utilities Impact:
  Full Depth Pavement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  City of Stromsburg, Cogent Comm. Inc. (Sprint & T-Mobile), Northern Natural Gas, Polk County RPPD, Vyve Broadband, Windstream Comm.

## Slide 41: St Libory North & South (MS) Project No.: NH-281-2(129); Control No.: 42826
Project Length: 6.3
Scope of Work:
  Resurfacing
  Culvert Extension/Replace
  Shoulder Work

## Slide 42: St Libory North & South (MS) Project No.: NH-281-2(129); Control No.: 42826
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 12/14/2023
Construction Timing: 4/1/2024 - 12/7/2024

## Slide 43: St Libory North & South (MS) Project No.: NH-281-2(129); Control No.: 42826
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Shoulder Work
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Charter Comm. (Spectrum), City of Grand Island, Howard Greeley RPPD, Lumen (CenturyLink), Nebraska PPD, Southern PPD

## Slide 44: Belvidere North Bridges (MS) Project No.: NH-81-1(123); Control No.: 42851
Project Length: 3 Bridge Locations
Scope of Work:
  Bridge Replacement
  Grading
  ITS/Lighting

## Slide 45: Belvidere North Bridges (MS) Project No.: NH-81-1(123); Control No.: 42851
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 12/14/2023
Construction Timing: 6/10/2024 - 6/21/2025

## Slide 46: Belvidere North Bridges (MS) Project No.: NH-81-1(123); Control No.: 42851
Anticipated Utilities Impact:
  Access Crossings
  Bridge Repair/Replacement
  Temp. Roads/Drives
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Glenwood Telephone, Great Plains Comm., Norris PPD, Viaero Fiber Net. (NE-CO Cell.), Windstream Comm.

## Slide 47: York - Utica Project No.: HSIP-80-8(165); Control No.: 42923
Project Length: 14.68
Scope of Work:
  Guardrail

## Slide 48: York - Utica Project No.: HSIP-80-8(165); Control No.: 42923
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  None
Letting Date: 12/14/2023
Construction Timing: 5/27/2024

## Slide 49: York - Utica Project No.: HSIP-80-8(165); Control No.: 42923
Anticipated Utilities Impact:
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Allo Comm., Black Hills Energy, Charter Comm. (Spectrum), City of York, Nebraska PPD, Norris PPD, NuStar Pipeline, OPTK Networks (NebraskaLink), Perennial PPD, Unite Private Net., Windstream Comm.

## Slide 50: Fullerton Wetland Mitigation Site Project No.: MISC-14-3(1016); Control No.: 42403B
Project Length: 0
Scope of Work:
  Grading

## Slide 51: Fullerton Wetland Mitigation Site Project No.: MISC-14-3(1016); Control No.: 42403B
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  None
Letting Date: 2/1/2024
Construction Timing: 4/1/2024

## Slide 52: Fullerton Wetland Mitigation Site Project No.: MISC-14-3(1016); Control No.: 42403B
Anticipated Utilities Impact:
  Grading
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  City of Fullerton, Cornhusker PPD, Loup River PPD, Lumen (CenturyLink), Vyve Broadband

## Slide 53: Kearney/Adams Co Line East (MS) Project No.: STP-74-4(111); Control No.: 42831
Project Length: 17.64
Scope of Work:
  Resurfacing
  Culvert Extension/Replace
  Bridge Repair

## Slide 54: Kearney/Adams Co Line East (MS) Project No.: STP-74-4(111); Control No.: 42831
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/1/2024
Construction Timing: 5/1/2024 - 10/31/2024

## Slide 55: Kearney/Adams Co Line East (MS) Project No.: STP-74-4(111); Control No.: 42831
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Culvert Extension/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Glenwood Telephone, Nebr. DNR (USGS), Southern PPD, Tallgrass Energy, Village of Ayr, Village of Holstein, Village of Roseland, Windstream Comm.

## Slide 56: District 4 - Districtwide Bridges (MS) Project No.: STP-NH-92-5(110); Control No.: 42897
Project Length: 8 Bridge Locations
Scope of Work:
  Bridge Repair
  Guardrail
  Grading

## Slide 57: District 4 - Districtwide Bridges (MS) Project No.: STP-NH-92-5(110); Control No.: 42897
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/1/2024
Construction Timing: 5/1/2024 - 10/31/2024

## Slide 58: District 4 - Districtwide Bridges (MS) Project No.: STP-NH-92-5(110); Control No.: 42897
Anticipated Utilities Impact:
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Charter Comm. (Spectrum), City of Ord, Great Plains Comm., Hamilton Telecom. (NCTC), Howard Greeley RPPD, Lumen (CenturyLink), Village of Cairo, Vyve Broadband, Black Hills Energy

## Slide 59: Minden - Gibbon Project No.: NH-80-6(116); Control No.: 42854
Project Length: 4.49
Scope of Work:
  Resurfacing
  Guardrail

## Slide 60: Minden - Gibbon Project No.: NH-80-6(116); Control No.: 42854
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Full Detour
Letting Date: 2/29/2024
Construction Timing: 5/13/2024

## Slide 61: Minden - Gibbon Project No.: NH-80-6(116); Control No.: 42854
Anticipated Utilities Impact:
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Dawson PPD, Frontier Comm., Hamilton Telecom. (NCTC), Lumen (CenturyLink)

## Slide 62: N-40 North Project No.: STP-10-2(123); Control No.: 42873
Project Length: 4.76
Scope of Work:
  Resurfacing
  Bridge Repair
  Guardrail

## Slide 63: N-40 North Project No.: STP-10-2(123); Control No.: 42873
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 2/29/2024
Construction Timing: 7/15/2024

## Slide 64: N-40 North Project No.: STP-10-2(123); Control No.: 42873
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Charter Comm. (Spectrum), City of Kearney, Dawson PPD, Frontier Comm., Great Plains Comm., Northwestern Energy, Unite Private Net., Vyve Broadband

## Slide 65: Wood River - Platte River Project No.: NH-80-6(119); Control No.: 42921
Project Length: 11.63
Scope of Work:
  Crack Seal

## Slide 66: Wood River - Platte River Project No.: NH-80-6(119); Control No.: 42921
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 6/20/2024
Construction Timing: 11/1/2024 - 3/31/2025

## Slide 67: Wood River - Platte River Project No.: NH-80-6(119); Control No.: 42921
Anticipated Utilities Impact:
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Central Platte NRD, Lumen (CenturyLink), Southern PPD

## Slide 68: Platte River - Phillips Project No.: NH-80-6(118); Control No.: 42920
Project Length: 7.7
Scope of Work:
  Crack Seal

## Slide 69: Platte River - Phillips Project No.: NH-80-6(118); Control No.: 42920
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/24/2023
Construction Timing: 11/1/2023 - 3/31/2024

## Slide 70: Platte River - Phillips Project No.: NH-80-6(118); Control No.: 42920
Anticipated Utilities Impact:
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Charter Comm. (Spectrum), City of Grand Island, Great Plains Comm., Hamilton Telecom. (NCTC), Lumen (CenturyLink), Nebraska PPD, Northwestern Energy, Southern PPD, Tallgrass Energy, Viaero Fiber Net. (NE-CO Cell.), Windstream Comm.

## Slide 71: Construction YEAR 2025
The following projects are anticipated to be let during 2025
Notes: Kathy Fischer or Rhett Robinson

## Slide 72: Hastings Southeast Project No.: S-6-4(1022); Control No.: 41086
Project Length: 2.43
Scope of Work:
  Urban Reconstruction
  Culvert Extension/Replace
  ITS/Lighting

## Slide 73: Hastings Southeast Project No.: S-6-4(1022); Control No.: 41086
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
  Full Detour
  Local Detour
Letting Date: 8/29/2024
Construction Timing: 4/1/2025-11/1/2026

## Slide 74: Hastings Southeast Project No.: S-6-4(1022); Control No.: 41086
Anticipated Utilities Impact:
  Urban Reconstruction
  New ROW
  Culvert Extension/Replacement
Anticipated Request from Utilities:
  Potholing Required
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Allo Comm., Black Hills Energy, Charter Comm. (Spectrum), City of Hastings, Cogent Comm. Inc. (Sprint & T-Mobile), Great Plains Comm., Nebraska PPD, OPTK Networks (NebraskaLink), Southern PPD, Verizon / MCI, Windstream Comm. & Zayo Group.

## Slide 75: Hastings Regional Center Spur Bridge Project No.: STP-S01C(102); Control No.: 42742
Project Length: 0
Scope of Work:
  Bridge Repair
  Guardrail
  Grading

## Slide 76: Hastings Regional Center Spur Bridge Project No.: STP-S01C(102); Control No.: 42742
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Full Detour
Letting Date: 8/29/2024
Construction Timing: 5/26/2025

## Slide 77: Hastings Regional Center Spur Bridge Project No.: STP-S01C(102); Control No.: 42742
Anticipated Utilities Impact:
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  City of Hastings, Verizon / MCI, Viaero Fiber Net. (NE-CO Cell.), Windstream Comm.

## Slide 78: Davenport West (MS) Project No.: STP-4-5(106); Control No.: 42778
Project Length: 12.9
Scope of Work:
  Resurfacing
  Culvert Extension/Replace

## Slide 79: Davenport West (MS) Project No.: STP-4-5(106); Control No.: 42778
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025-10/31/2025

## Slide 80: Davenport West (MS) Project No.: STP-4-5(106); Control No.: 42778
Anticipated Utilities Impact:
  Culvert Extension/Replace
  Guardrail
  Bridge Repair/Replace
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Nebraska PPD, South Central PPD, Tallgrass Energy, Viaero Fiber Net. (NE-CO Cell.), Windstream Comm.

## Slide 81: Stromsburg North Project No.: NH-STP-81-2(154); Control No.: 42782A
Project Length: 4.28
Scope of Work:
  Resurfacing
  Pavement Repairs
  Shoulder Work

## Slide 82: Stromsburg North Project No.: NH-STP-81-2(154); Control No.: 42782A
Status: Preparing for Bid
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 4/1/2024-10/31/2024

## Slide 83: Stromsburg North Project No.: NH-STP-81-2(154); Control No.: 42782A
Anticipated Utilities Impact:
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  City of Stromsburg, Cogent Comm. Inc. (Sprint & T-Mobile), Northern Natural Gas, Polk County RPPD, Vyve Broadband, Windstream Comm.

## Slide 84: Hazard East (MS) Project No.: NH-2-4(111); Control No.: 42786
Project Length: 6.25
Scope of Work:
  Resurfacing
  Bridge Repair
  Guardrail

## Slide 85: Hazard East (MS) Project No.: NH-2-4(111); Control No.: 42786
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025-10/31/2025

## Slide 86: Hazard East (MS) Project No.: NH-2-4(111); Control No.: 42786
Anticipated Utilities Impact:
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Charter Comm. (Spectrum), City of Loup City, Custer PPD, Hamilton Telecom. (NCTC), Loup Valley RPPD, Lumen (CenturyLink), Nebr. DNR (USGS), Viaero Fiber Net. (NE-CO Cell.), Village of Hazard

## Slide 87: In Fairmont & East (MS) Project No.: STP-6-5(117)4; Control No.: 42813
Project Length: 11.85
Scope of Work:
  Resurfacing
  Bridge Repair
  Guardrail

## Slide 88: In Fairmont & East (MS) Project No.: STP-6-5(117)4; Control No.: 42813
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 4/15/2025-11/2/2025

## Slide 89: In Fairmont & East (MS) Project No.: STP-6-5(117)4; Control No.: 42813
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Culvert Extension/Replacement
  Guardrail
Anticipated Request from Utilities:
  Locates
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Glenwood Telephone, Lumen (CenturyLink), NuStar Pipeline, Perennial PPD, Unite Private Net., Verizon / MCI, Viaero Fiber Net. (NE-CO Cell.), Village of Exeter, Village of Fairmont, Windstream Comm., Zayo Group

## Slide 90: S. Jct. N-58 - N-92 (MS) Project No.: STP-11-2(122); Control No.: 42814
Project Length: 11.98
Scope of Work:
  Resurfacing
  Bridge Repair
  Culvert Extension/Replace

## Slide 91: S. Jct. N-58 - N-92 (MS) Project No.: STP-11-2(122); Control No.: 42814
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/13/2025-11/2/2025

## Slide 92: S. Jct. N-58 - N-92 (MS) Project No.: STP-11-2(122); Control No.: 42814
Anticipated Utilities Impact:
  Lighting
  Bridge Repair/Replacement
  Culvert Extension/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Hamilton Telecom. (NCTC), Howard Greeley RPPD, Lumen (CenturyLink), Nebr DNR (USGS), Nebraska PPD, Viaero Fiber Net. (NE-CO Cell.), Village of Dannebrog

## Slide 93: Central City East (MS) Project No.: NH-30-5(136); Control No.: 42818
Project Length: 8.23
Scope of Work:
  Resurfacing
  Grading
  Full Depth Pavement

## Slide 94: Central City East (MS) Project No.: NH-30-5(136); Control No.: 42818
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Local Detour
Letting Date: 10/3/2024
Construction Timing: 6/16/2025-11/22/2025

## Slide 95: Central City East (MS) Project No.: NH-30-5(136); Control No.: 42818
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  New ROW
  Lighting
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  City of Central City, Clarks Telecom., Cogent Comm. Inc. (Sprint & T-Mobile), Great Plains Comm., Hamilton Telecom. (NCTC), Lumen (CenturyLink), Northeast Nebr. Telephone Co. , Southern PPD, Vyve Broadband

## Slide 96: Clay Center East Project No.: STP-41-5(108); Control No.: 42829
Project Length: 11.62
Scope of Work:
  Resurfacing
  Culvert Extension/Replacement

## Slide 97: Clay Center East Project No.: STP-41-5(108); Control No.: 42829
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 6/23/2025

## Slide 98: Clay Center East Project No.: STP-41-5(108); Control No.: 42829
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, City of Clay Center, Glenwood Telephone, South Central PPD, Tallgrass Energy, Unite Private Net., Windstream Comm.

## Slide 99: Strang Spur East Project No.: STP-74-5(112); Control No.: 42832
Project Length: 11.74
Scope of Work:
  Resurfacing
  Culvert Extension/Replacement

## Slide 100: Strang Spur East Project No.: STP-74-5(112); Control No.: 42832
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 7/22/2025

## Slide 101: Strang Spur East Project No.: STP-74-5(112); Control No.: 42832
Anticipated Utilities Impact:
  New ROW
  Culvert Extension/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Glenwood Telephone, Little Blue NRD, Perennial PPD, Tallgrass Energy, Unite Private Net., Village of Ohiowa, Windstream Comm.

## Slide 102: Ong Spur - US-81 (MS) Project No.: STP-74-5(113); Control No.: 42833
Project Length: 13.29
Scope of Work:
  Resurfacing
  Bridge Repair
  Guardrail

## Slide 103: Ong Spur - US-81 (MS) Project No.: STP-74-5(113); Control No.: 42833
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025-10/31/2025

## Slide 104: Ong Spur - US-81 (MS) Project No.: STP-74-5(113); Control No.: 42833
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Guardrail
  Shoulder Work
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Black Hills Energy, Glenwood Telephone, Great Plains Comm., Perennial PPD, Tallgrass Energy, Unite Private Net., Village of Shickley, Windstream Comm.

## Slide 105: Odessa - Kearney East Crossover (MS) Project No.: NH-80-5(84); Control No.: 42852A
Project Length: 9.29
Scope of Work:
  Full Depth Pavement
  Grading
  ITS/Lighting

## Slide 106: Odessa - Kearney East Crossover (MS) Project No.: NH-80-5(84); Control No.: 42852A
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/28/2025
Construction Timing: 9/1/2026-10/31/2026

## Slide 107: Odessa - Kearney East Crossover (MS) Project No.: NH-80-5(84); Control No.: 42852A
Anticipated Utilities Impact:
  Lighting
  Grading
  Temp. Roads/Drives
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:

## Slide 108: Davenport East (MS) Project No.: STP-4-5(107); Control No.: 42875
Project Length: 12.95
Scope of Work:
  Resurfacing
  Culvert Extension/Replace
  Bridge Repair

## Slide 109: Davenport East (MS) Project No.: STP-4-5(107); Control No.: 42875
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025-10/31/2025

## Slide 110: Davenport East (MS) Project No.: STP-4-5(107); Control No.: 42875
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Culvert Extension/Replacement
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Glenwood Telephone, Great Plains Comm., Nebraska PPD, Norris PPD, NuStar Pipeline, Tallgrass Energy, Unite Private Net., Viaero Fiber Net. (Ne-Co Cell.), Village of Davenport, Windstream Comm.

## Slide 111: York Bypass Bridges Project No.: NH-81-2(149); Control No.: 42889
Project Length: 0
Scope of Work:
  Bridge Repair
  Guardrail

## Slide 112: York Bypass Bridges Project No.: NH-81-2(149); Control No.: 42889
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025

## Slide 113: York Bypass Bridges Project No.: NH-81-2(149); Control No.: 42889
Anticipated Utilities Impact:
  Bridge Repair/Replacement
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Allo Comm., Charter Comm. (Spectrum), Nebraska PPD, Unite Private Net., Verizon / MCI, Windstream Comm.

## Slide 114: Kearney East Bridges (MS) Project No.: STP-NH-10-2(125); Control No.: 42890
Project Length: 4 locations
Scope of Work:
  Bridge Repair
  Guardrail
  Resurfacing

## Slide 115: Kearney East Bridges (MS) Project No.: STP-NH-10-2(125); Control No.: 42890
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 6/17/2025-8/31/2025

## Slide 116: Kearney East Bridges (MS) Project No.: STP-NH-10-2(125); Control No.: 42890
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets TBD
  Special Provisions TBD
Utilities Involved:
  Allo Comm., Black Hills Energy, Charter Comm. (Spectrum), City of Kearney, Cogent Comm. Inc. (Sprint & T-Mobile), Dawson PPD, Great Plains Comm., Nebraska PPD, Northwestern Energy, Unite Private Net., Verizon / MCI , Viaero Fiber Net. (NE-CO Cell.), Winds

## Slide 117: District 4 Wetland Bank Project No.: MISC-40(65); Control No.: 42891
Project Length: 0
Scope of Work:
  Grading

## Slide 118: District 4 Wetland Bank Project No.: MISC-40(65); Control No.: 42891
Status: Planning
Right-of-Way: In Progress
Traffic Impacts:
  None
Letting Date: 8/29/2024
Construction Timing: 5/1/2025-10/31/2025

## Slide 119: District 4 Wetland Bank Project No.: MISC-40(65); Control No.: 42891
Anticipated Utilities Impact:
  Grading
  No Impacts
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Southern PPD, Viaero Fiber Net. (NE-CO Cell.)

## Slide 120: Elm Creek - Miller (MS) Project No.: STP-183-2(111); Control No.: 42898
Project Length: 14.42
Scope of Work:
  Resurfacing
  Bridge Replacement
  Grading

## Slide 121: Elm Creek - Miller (MS) Project No.: STP-183-2(111); Control No.: 42898
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025-10/31/2025

## Slide 122: Elm Creek - Miller (MS) Project No.: STP-183-2(111); Control No.: 42898
Anticipated Utilities Impact:
  Bridge Repair/Replacement
  Culvert Extension/Replacement
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets TBD
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Charter Comm. (Spectrum), Cogent Comm. Inc. (Sprint & T-Mobile), Dawson PPD, Frontier Comm., Great Plains Comm., Lumen (CenturyLink), Nebraska PPD, OPTK Networks (NebraskaLink), Tallgrass Energy, Verizon / MCI, Village of Elm Creek, Vi

## Slide 123: Chapman West (MS) Project No.: NH-30-5(139); Control No.: 42929
Project Length: 8.03
Scope of Work:
  Resurfacing
  Grading
  Full Depth Pavement

## Slide 124: Chapman West (MS) Project No.: NH-30-5(139); Control No.: 42929
Status: Design
Right-of-Way: In Progress
Traffic Impacts:
  Local Detour
Letting Date: 12/12/2024
Construction Timing: 5/1/2025-10/31/2025

## Slide 125: Chapman West (MS) Project No.: NH-30-5(139); Control No.: 42929
Anticipated Utilities Impact:
  Turn Lane Add/Adjust
  Lighting
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets TBD
  Special Provisions TBD
Utilities Involved:
  AT&T Comm., Black Hills Energy, Charter Comm. (Spectrum), City of Grand Island, Cogent Comm. Inc. (Sprint & T-Mobile), Great Plains Comm., Lumen (CenturyLink), Southern PPD, Tallgrass Energy, Village of Chapman,
  Vyve Broadband

## Slide 126: Kearney East Project No.: STP-30-4(167); Control No.: 42969
Project Length: 1.88
Scope of Work:
  ITS/Lighting

## Slide 127: Kearney East Project No.: STP-30-4(167); Control No.: 42969
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 4/1/2025

## Slide 128: Kearney East Project No.: STP-30-4(167); Control No.: 42969
Anticipated Utilities Impact:
  Lighting
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets TBD
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Cable USA, Charter Comm. (Spectrum), City of Kearney, Cogent Comm. Inc. (Sprint & T-Mobile), Frontier Comm., Great Plains Comm., Nebraska PPD, Northwestern Energy, OPTK Networks (NebraskaLink), Unite Private Net., Verizon / MCI , Winds

## Slide 129: District 4 High Mast Tower Replacement Project No.: STP-80-7(175); Control No.: 43011
Project Length: 0
Scope of Work:
  ITS/Lighting

## Slide 130: District 4 High Mast Tower Replacement Project No.: STP-80-7(175); Control No.: 43011
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  Phase Traffic Control
Letting Date: 8/29/2024
Construction Timing: 5/1/2025

## Slide 131: District 4 High Mast Tower Replacement Project No.: STP-80-7(175); Control No.: 43011
Anticipated Utilities Impact:
  Lighting
  Grading
Anticipated Request from Utilities:
  Potholing TBD
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  No K-Sheets Required
  Special Provisions TBD
Utilities Involved:
  I-80, Phillips Intx.: Black Hills Energy, Hamilton Telecom., Southern PPD
  US-81 & US-136: Norris PPD, Tallgrass Energy, Viaero Fiber (NE-CO-Cell.), Windstream Comm.

## Slide 132: Hampton - York Project No.: HSIP-80-7(174); Control No.: 42990
Project Length: 15
Scope of Work:
  Guardrail

## Slide 133: Hampton - York Project No.: HSIP-80-7(174); Control No.: 42990
Status: Design
Right-of-Way: Not Required
Traffic Impacts:
  None
Letting Date: 10/3/2024
Construction Timing: 4/1/2025

## Slide 134: Hampton - York Project No.: HSIP-80-7(174); Control No.: 42990
Anticipated Utilities Impact:
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
  K-Sheets TBD
  Special Provisions TBD
Utilities Involved:
  Black Hills Energy, Hamilton Telecom. (NCTC), Mainstay Comm., Southern PPD

## Slide 135: Questions & Wrap Up
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 136: Any final Questions?
Ask them now!
If you have questions after this meeting, or would like to view more detailed project maps, please reach out to your utility coordinator.
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 137: Have a Question about a project your Utility is involved in?
Contact your district’s utility coordinator!
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 138: We need your feedback
Your valuable feedback helps these meetings – and NDOT’s utility coordination program – be better.
Use your phone’s camera to scan this QR code or use our paper survey.
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 139: Visit our Website
Visit NDOT.info/utility for more information on:
Utility accommodation
Permitting
Coordination
Project information
Reimbursements
Additional information
Notes: HDR (Kristen, Amanda or Alyssa)

## Slide 140: Thank You
Notes: HDR (Kristen, Amanda or Alyssa)