## Directions
Directions for Completing Fee Proposal Workbooks
** HIDE TAB / DO NOT PRINT **
General Information
This workbook has been designed to simplify the cost estimating process and to create a standard approach for Consultants, Local Public Agencies (LPA) and Nebraska Department of Transportation--so all can be working from the same page. For NDOT projects, Consultants will submit their completed ICE workbook to the Agreements Engineer. For LPA projects, Consultants will submit the completed ICE workbook to the LPA Responsible Charge (RC). The LPA may not receive the Consultants ICE until the LPA has received from NDOR written notice approving the LPA's ICE. Start by opening the tab labeled "Staffing Plan" and following the directions listed below.
Staffing Plan
FOR HEADER:
● This worksheet is the source of all header info for the rest of the workbook. Enter general project type at top right.
● Enter any missing project information at the top of this worksheet. This information will self-populate the remaining sheets.
● If desired, add your company's logo in place of NDOT's (right-click on logo and select Change Picture).
FOR TABLE:
● This worksheet calculates direct labor costs and serves as the Staffing Plan.
● The Blended Rates Worksheet is used to:
(1) determine rates for personnel categories with more than one individual,
(2) to document the Consultant's proposed project staffing.
● Begin by editing as necessary the abbreviation codes and classifications in the first table.
● Next, assign values for your firm's most recent audited Overhead Rate, and the Fee for Profit Rate calculated from the NDOT Fee for Profit Worksheet (available on the NDOT website)., and FCCM if applicable.
● Assign project staff to applicable personnel classifications.
● Enter direct salary rates used by your company for each employee.
● Assign a value to the % Assigned column based on the estimated percentage of hours that each employee will use.
● The total of % Assigned must equal 100% for each personnel classification category.
● Hide empty rows if needed to improve the look of printed page.
Estimate of Hours
● Descriptions of the tasks are listed in the Schedule of Services. Edit descriptions and rows as necessary.
● Assign hours to tasks based on personnel classifications provided, and the project requirements.
● Salary rates will be added on the Staffing Plan worksheet, and will self-populate the other sheets.
● Hide or unhide rows as necessary.
Direct Expenses
● Subconsultants must be listed as a direct expense. Sub scope and cost proposals must also be submitted.
Project Cost Breakdown
All data on this tab should self-populate from other sheets in the workbook, including Overhead and the Fee for Profit (these percentages are assigned on the Staffing Plan sheet.)
Negotiations
Comparison of hours - used for negotiating prime and sub hours

## Staffing Plan
Staffing Plan (CPFF) | [5 empty] | Fee for NEPA for Scoping | [8 empty] | n | <-- Is this workbook for a subconsultant? (y/n)
0
|  | Project Name: | [6 empty] | Project Number:
|  | Consultant: | [6 empty] | Control Number:
|  | Consultant PM: | [6 empty] | Example: John Doe, 402-867-5309, jd@consultants.com | [5 empty] | Replace NDOT logo with Firm's logo, if desired
|  | LPA RC: | [6 empty] | Example: Sue Jones, 402-777-0000, sue@lpa.gov | [5 empty] | (right-click on logo and select 'change picture')
|  | NDOT PC: | [6 empty] | Example: Jane Smith, 402-479-0001, jane.smith@nebraska.gov
Date:
# | Code | Classification |  | # | Code | Classification |  |  |  | Overhead Rate [1] |  |  |  |  | User can change labor codes and classifications, overhead, profit rate, FCCM,
1 | PR | Principal |  | 6 | DES | Designer | [5 empty] | % |  |  | and name, title, salary rate, and % assigned in Blended Rate Table
2 | PM | Program Manager |  | 7 | TECH | Technician |  |  |  | Fee for Profit Rate [2]
3 | SENG | Sr. Engineer |  | 8 | ADM | Administrative | [5 empty] | %
4 | ENG | Engineer |  | 9 | UD1 | User Defined 1 |  |  |  | FCCM (if applicable)
5 | SDES | Sr. Designer |  | 10 | UD2 | User Defined 2 | [5 empty] | %
BLENDED RATES TABLE | [12 empty] | Template: T-WB-B-2 LPA PE Scoping (rev 10-07-2025) CPFF | 2025-10-07 |  | <-- template revision date (xx/yy/zz)
|  |  | Job Title & Certifications [3] |  |  |  |  | Current Actual Salary Rate/Hr [4] |  |  | % Assigned |  |  | B-2 LPA PE Scoping |  |  | <-- template name (ex. C2 Bridge Design
Employee Name
Principal
Hide empty rows if needed to improve printing
[7 empty] | Blended Rate: | 0 |  |  | 0
Program Manager
[7 empty] | Blended Rate: | 0 |  |  | 0
Sr. Engineer
[7 empty] | Blended Rate: | 0 |  |  | 0
Engineer
[7 empty] | Blended Rate: | 0 |  |  | 0
Sr. Designer
[7 empty] | Blended Rate: | 0 |  |  | 0
Designer
[7 empty] | Blended Rate: | 0 |  |  | 0
Technician
[7 empty] | Blended Rate: | 0 |  |  | 0
Administrative
[7 empty] | Blended Rate: | 0 |  |  | 0
User Defined 1
[7 empty] | Blended Rate: | 0 |  |  | 0
User Defined 2
[7 empty] | Blended Rate: | 0 |  |  | 0
[1] Enter firms most recent Audited Overhead Rate.
[2] Enter the Fee for Profit Rate provided by NDOT.
[3] Input actual employee job title/classification as designated by the firm. Also enter in any certifications that employee holds.
[4] Enter employee's current and verifiable actual hourly salary rate.
FCCM = Facilities Capital Cost of Money.

## Est. of Hours
Estimate of Hours | [5 empty] | Fee for NEPA for Scoping
0
|  | Project Name: | 0 |  |  |  |  | Project Number: | 0
|  | Consultant: | 0 |  |  |  |  | Control Number: | 0
|  | Consultant PM: | 0 | [12 empty] | Hide blank rows as desired.
|  | LPA RC: | 0
|  | NDOT PC: | 0 | [12 empty] | User can create major and sub TASKS in columns A & B.
|  | Date: | 0 | [12 empty] | User can input hours for each personnel classification
TASKS |  |  |  | PERSONNEL CLASSIFICATIONS
|  |  |  | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2 | Total
I. Development of Scope of Services for NEPA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
1 | Project Management | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Prepare Project Description | [12 empty] | 0
3 | Prepare Project Details | [12 empty] | 0
4 | Prepare Purpose & Need | [12 empty] | 0
5 | Scope of services and corresponding workbook for NEPA | [12 empty] | 0
6 | Develop a schedule | [12 empty] | 0
7 | PCM 0 | [12 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
II. Site Visit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
1 | Site visit | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Travel | [12 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
III. User Defined Task 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
1 | Plan-In-Hand Revisions | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Plan Production / Printing | [12 empty] | 0
3 | Quantities | [12 empty] | 0
4 | QA/QC | [12 empty] | 0
5 | Floodplain Certification | [12 empty] | 0
6 | Miscellaneous | [12 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
IV. User Defined Task 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
1 | [13 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | [13 empty] | 0
3 | [13 empty] | 0
4 | [13 empty] | 0
5 | [13 empty] | 0
6 | [13 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
V. User Defined Task 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
1 | [13 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | [13 empty] | 0
3 | [13 empty] | 0
4 | [13 empty] | 0
5 | [13 empty] | 0
6 | [13 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
VI. User Defined Task 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
1 | EXAMPLE | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | EXAMPLE | [12 empty] | 0
3 | EXAMPLE | [12 empty] | 0
4 | EXAMPLE | [12 empty] | 0
5 | EXAMPLE | [12 empty] | 0
6 | EXAMPLE | [12 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
VII. User Defined Task 7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
VIII. User Defined Task 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
IX. User Defined Task 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
X. User Defined Task 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
XI. User Defined Task 11 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
XII. User Defined Task 12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
XIII. User Defined Task 13 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
XIV. User Defined Task 14 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | match | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total Days |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | PR | PM | SENG | ENG | SDES | DES | TECH | ADM | UD1 | UD2
[17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Direct Expenses
Direct Expenses |  |  |  | Fee for NEPA for Scoping
0
| Project Name: | 0 |  |  |  | Project Number: | 0
| Consultant: | 0 |  |  |  | Control Number: | 0
| Consultant PM: | 0
| LPA RC: | 0
| NDOT PC: | 0
| Date: | 0
Subconsultants: | [7 empty] | Amount
[7 empty] | Subtotal | 0
Printing and Reproduction: |  |  |  |  | Qty | Unit Cost |  | Amount
0
0
0
0
0
0
0
0
0
0
0
0
0
[7 empty] | Subtotal | 0
Mileage/Travel: |  |  |  |  | Qty | Unit Cost |  | Amount
Mileage/Travel: | [5 empty] | 0.725 |  | 0 | effective 1/1/2026 = $0.725
0
0
0
0
0
0
0
0
0
0
0
[7 empty] | Subtotal | 0
Lodging/Meals: |  |  |  |  | Qty | Unit Cost |  | Amount
Motel - Standard Rate $110+tax | [5 empty] | 130 |  | 0 | effective 10/1/2025: $110 + tax = $130
Motel - Omaha/Douglas Co. $122+tax | [5 empty] | 145 |  | 0 | effective 10/1/2025: $122 + tax = $145
Meals & Incidentals (70% GSA Standard Rate, full days) | [5 empty] | 47.6 |  | 0 | effective 10/1/2025: 0.7*$68 = $47.60
Meals & Incidentals (70% GSA Standard Rate, 1st & last days) | [5 empty] | 35.7 |  | 0 | effective 10/1/2025: 0.7*$51 = $37.50
Meals & Incidentals (70% GSA Rate, full days, Omaha/Douglas Co.) | [5 empty] | 56 |  | 0 | effective 10/1/2025: 0.7*$80 = $56.00
Meals & Incidentals (70% GSA Rate, 1st & last days, Omaha/Douglas Co.) | [5 empty] | 42 |  | 0 | effective 10/1/2025: 0.7*$60 = $42.00
0
0
0
0
0
0
0
[7 empty] | Subtotal | 0
Other Miscellaneous Costs: |  |  |  |  | Qty | Unit Cost |  | Amount
0
0
0
0
0
0
0
0
0
0
0
0
[7 empty] | Subtotal | 0
TOTAL DIRECT EXPENSES | [7 empty] | 0
Per Diem Rates: |  |  | http://www.gsa.gov/portal/category/104711
Mileage Rates: |  |  | http://www.gsa.gov/portal/category/104715
Example Expense Costs - Expenses shown below are examples, and may not represent approved rates.
Subconsultants: | [7 empty] | Amount
IMA Sub, Inc. (don't forget to include supporting info such as sub proposal/scope) | [7 empty] | 2300
[7 empty] | Subtotal | 2300
Printing and Reproduction: |  |  |  |  | Qty | Unit Cost |  | Amount
86 - 34"x22" plan sheets plotted 2 times @ $1.50/plot |  |  |  |  | 172 | 1.5 |  | 258
86 - 11"x17" half size plan sheets plotted 10 times @ $0.08/sheet |  |  |  |  | 860 | 0.08 |  | 68.8
10 displays, 32"x40" @ $1.70/SF mounted |  |  |  |  | 88.89 | 1.7 |  | 151.113
5,000 black & white copies @ $0.05/sheet |  |  |  |  | 5000 | 0.05 |  | 250
2,000 color copies @ $0.18/sheet |  |  |  |  | 2000 | 0.18 |  | 360
0
[7 empty] | Subtotal | 1087.913
Mileage/Travel: |  |  |  |  | Qty | Unit Cost |  | Amount
2 trips to Lincoln @ 120 mi/trip |  |  |  |  | 240 | 0.58 |  | 139.2
6 trips to Public Works Department @ 14 mi/trip @ $0.575/mi |  |  |  |  | 84 | 0.58 |  | 48.72
4 trips to project site @ 24 mi/trip |  |  |  |  | 96 | 0.58 |  | 55.68
10 miles traveled on the project site @ $0.575/mi |  |  |  |  | 10 | 0.58 |  | 5.8
0
[7 empty] | Subtotal | 249.4
Lodging/Meals: |  |  |  |  | Qty | Unit Cost |  | Amount
Hotel (16 nights @ $98 + $18 tax) |  |  |  |  | 16 | 116 |  | 1856
Meals (6 full days @ $38/day) |  |  |  |  | 6 | 38 |  | 228
Meals (4 first/last days @ $28/day) |  |  |  |  | 4 | 28 |  | 112
[7 empty] | Subtotal | 2196
Other Miscellaneous Costs: |  |  |  |  | Qty | Unit Cost |  | Amount
Miscellaneous Postage, Mailing, Deliveries Etc. |  |  |  |  | 1 | 25.65 |  | 25.65
0
0
[7 empty] | Subtotal | 25.65

## Notes-Assumptions
Notes & Assumptions |  |  | Fee for NEPA for Scoping
0
| Project Name: | 0 |  | Project Number: | 0
| Consultant: | 0 |  | Control Number: | 0
| Consultant PM: | 0
| LPA RC: | 0
| NDOT PC: | 0
| Date: | 0
Notes & Assumptions

## Project Cost Breakdown
Project Cost & Breakdown | [6 empty] | Fee for NEPA for Scoping
0
|  | Project Name: | 0 | [7 empty] | Project Number: | 0
|  | Consultant: | 0 | [7 empty] | Control Number: | 0 |  | There are no editable cells
|  | Consultant PM: | 0 | [10 empty] | in this worksheet.
|  | LPA RC: | 0
|  | NDOT PC: | 0
|  | Date: | 0
DIRECT LABOR COSTS
Classification | [7 empty] | Hours |  | Rate |  |  | Amount
Principal | [7 empty] | 0 |  | 0 |  |  | 0
Program Manager | [7 empty] | 0 |  | 0 |  |  | 0
Sr. Engineer | [7 empty] | 0 |  | 0 |  |  | 0
Engineer | [7 empty] | 0 |  | 0 |  |  | 0
Sr. Designer | [7 empty] | 0 |  | 0 |  |  | 0
Designer | [7 empty] | 0 |  | 0 |  |  | 0
Technician | [7 empty] | 0 |  | 0 |  |  | 0
Administrative | [7 empty] | 0 |  | 0 |  |  | 0
User Defined 1 | [7 empty] | 0 |  | 0 |  |  | 0
User Defined 2 | [7 empty] | 0 |  | 0 |  |  | 0
|  |  | 0 | 0 | 0 | 0 |  | 0 |  |  |  | Subtotal | 0
DIRECT EXPENSES | [12 empty] | Amount
Subconsultants: | [12 empty] | 0
Printing And Reproduction: | [12 empty] | 0
Mileage/Travel: | [12 empty] | 0
Lodging/Meals: | [12 empty] | 0
Other Miscellaneous Costs: | [12 empty] | 0
[12 empty] | Subtotal | 0
TOTAL PROJECT COSTS | [12 empty] | Amount |  | Fees & Payments Exhibit Values
Direct Labor Costs | [12 empty] | 0 |  | 0 | for actual direct labor costs
Labor Cost Escalation Factor for Multi-year Projects (if allowed): | [6 empty] | n | 2 | 4% |  | / year = | 0% | 0
Overhead @ | 0% | [11 empty] | 0 |  | 0 | for indirect labor costs and direct expenses
Facility Capital Cost of Money (FCCM) @ | [5 empty] | 0% | (labor costs x FCCM%) | [5 empty] | 0 |  | 0 | for a fixed fee for profit
Direct Expenses | [12 empty] | 0 |  | 0 | Total
Fee for Profit Rate @ |  |  |  | 0% | [8 empty] | 0
[12 empty] | TOTAL COST | 0
LABOR COST BY MAJOR TASKS | [5 empty] | Direct Labor |  | Overhead+FCCM |  |  | Profit |  | Amount
I. Development of Scope of Services for NEPA | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0
II. Site Visit | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0
III. User Defined Task 3 | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0
IV. User Defined Task 4 | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0 |  | NDOT can hide this section if it is not needed
V. User Defined Task 5 | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0
VI. User Defined Task 6 | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0
VII. User Defined Task 7 | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0
VIII. User Defined Task 8 | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0
IX. User Defined Task 9 | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0
X. User Defined Task 10 | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0
XI. User Defined Task 11 | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0
XII. User Defined Task 12 | [5 empty] | 0 |  | 0 |  |  | 0 |  | 0
[6 empty] | 0 |  | 0 |  |  | 0 |  | 0
SUMMARY FOR MULTIPLE WORKBOOKS
[15 empty] | FF | Direct labor | Overhead/FCCM/Direct costs
[12 empty] | Exhibit "?" Subtotal: | 0 |  | 0 | 0 | 0
[12 empty] | (Sub: subconsultant name) Service Category - Exhibit "?" Subtotal: | 0
[12 empty] | (Sub: subconsultant name) Service Category - Exhibit "?" Subtotal: | 0
[12 empty] | (Sub: subconsultant name) Service Category - Exhibit "?" Subtotal: | 0
[12 empty] | Total Agreement Amount: | 0 |  | 0 | 0 | 0
Reset print area if you want to use/see the SUMMARY FOR MULTIPLE WORKBOOKS table

## Negotiations
Negotiations - Comparison of Hours
0
|  | Project Number: | 0
|  | Control Number: | 0 | [6 empty] | Proposal Above (+), Below (-) NDOT's ICE |  | Negotiated Above (+), Below (-) NDOT's ICE
| 1) | Paste "values" beginning at row 12 for each Subconsultant
| 2) | Paste "values" from NDOT ICE workbook beginning at N12
| 3) | Enter negotiated hours for Prime and Subs (if applicable)
TASKS |  |  |  | Consultant's combined Fee Proposal | [6 empty] | NDOT |  | Negotiated | Negotiated Fee Proposal
|  |  |  | PRIME | SUB-1 | SUB-2 | SUB-3 | SUB-4 | TOTAL | % | ICE | % | TOTAL | PRIME | SUB-1 | SUB-2 | SUB-3 | SUB-4 | Negotiation Notes/Summary
I. Development of Scope of Services for NEPA |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
1 | Project Management |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
2 | Prepare Project Description |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
3 | Prepare Project Details |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
4 | Prepare Purpose & Need |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
5 | Scope of services and corresponding workbook for NEPA |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
6 | Develop a schedule |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
7 | PCM 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
II. Site Visit |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
1 | Site visit |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
2 | Travel |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
III. User Defined Task 3 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
1 | Plan-In-Hand Revisions |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
2 | Plan Production / Printing |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
3 | Quantities |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
4 | QA/QC |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
5 | Floodplain Certification |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
6 | Miscellaneous |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
IV. User Defined Task 4 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
2 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
3 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
4 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
5 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
6 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
V. User Defined Task 5 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
2 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
3 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
4 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
5 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
6 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
VI. User Defined Task 6 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
1 | EXAMPLE |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
2 | EXAMPLE |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
3 | EXAMPLE |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
4 | EXAMPLE |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
5 | EXAMPLE |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
6 | EXAMPLE |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
VII. User Defined Task 7 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
VIII. User Defined Task 8 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
IX. User Defined Task 9 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
X. User Defined Task 10 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
XI. User Defined Task 11 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
XII. User Defined Task 12 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
XIII. User Defined Task 13 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
XIV. User Defined Task 14 |  |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0% | 0
Total Hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 |  | 0 | 0 | 0 | 0
[11 empty] | #DIV/0! |  | (% above NDOT Estimate)